## Checklist
Object Detection with Jetson Nano integrated in a Kuka KR6
Name, Vorname |  |  |  | cc: Firmenbetreuer
Matr.-Nr | <1234567> |  |  | Projektpartner
Erstprüfer
Checklist
update every day!
No. | Topic | done | date
First two weeks
1 | read ProjectManagement/BestPractice.pdf | 1st Week | 25.9.2025
2 | fulfill author.xlsx |  | 28.9.2025
3 | Install TeXLive |  | 25.9.2025
4 | install TeXStudio |  | 25.9.2025
5 | install Sumatrapdf |  | 28.9.2025
6 | configure TeXStudio |  | 28.9.2025
7 | test template report |  | 25.9.2025
8 | test template poster |  | 25.9.2025
9 | test template Presentations/template |  | 25.9.2025
10 | install doxygen |  | 25.9.2025
11 | readme.md |  | 25.9.2025
12 | literature research | 2nd week | 2.10.2025
13 | bib file |  | 2.10.2025
14 | bibliography |  | 2.10.2025
15 | pdf files |  | 2.10.2025
16 | presentation "Literature" |  | 2.10.2025
17 | challenges with citations |  | 2.10.2025
18 | write n introduction with citations |  | 6.10.2025
19 | presentation "Introduction" |  | 6.10.2025
20 | project plan | 3rd week | 13.10.2025
21 | fulfill the list "Resulting Objects" |  | 13.10.2025
22 | presentation "Project Plan" |  | 13.10.2025
23 | Readme.md |  | 13.10.2025
Processing the project
24 | update project plan | 4th week | 20.10.2025
25 | update the list "Resulting Objects" |  | 20.10.2026
26 | presentation "Project Plan" II |  | 20.10.2027
27 | rename all tex files along the project plan |  | 20.10.2028
28 | delete or add additional TeX or Python projects, e.g. Manual |  | 20.10.2029
29 | List of Material |  | 27.10.2025
30 | Manual |  | 27.10.2026
31 | domain knowledge | 5th week | 27.10.2027
32 | algorithm |  | 27.10.2028
33 | tools |  | 27.10.2029
34 | methodology |  | 27.10.2030
35 | database | 6th week
36 | database description
37 | database discussion
38 | Homework "Literature" | 7th week
39 | Homework "John Ousterhout"
40 | updated README.md
41 | updated Project plan | 8th weeek
42 | updated Resulting objects
43 | Evaluation
44 | Validation
45 | Homework "UpdatedLiterature" | 9th week
46 | Development structure
47 | Development Environment
48 | From Development to Deployment | 10 th weeek
49 | Flow Chart
50 | tests
Final stage
51 | check: all website as pdf-file?
52 | check: all pdfs in the folder Documents?
53 | check: all images okay?
54 | check spelling
55 | check: poster?
56 | print poster
57 | check: GitHub project
58 | ready minimal one day before deadline
59
60
61
62

## Projekt Plan V1.0 (deut.)
Das Liebesleben der Maikäfer bei Nacht
|  | KW | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 26 | 27 | ... | 30
|  | lfd. Woche | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 16 | 17 | ... | 20
TP-Nr. | TP-Name | Dauer
1 | Einarbeitung / Literatur | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Verfassen PA / BT / DA / MT | ...
15 | Durchsicht | 2
16 |  | 1.5
17 | Kolloquium | 1
| Urlaub / Feiertage | [5 empty] | Geburt |  |  | Ostern |  | Pfingsten
| Anmeldung / Abgabe | [7 empty] | 34. März |  |  |  |  | 34. Juli
Besprechungen
PJ = Projekt
| TP = Teilprojekt | [8 empty] | x = f(Studiengang)
Anmeldung
Abgabe
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.3 / 29.02.2025
Persönliche Daten
Vorläufiger Titel
der Arbeit
Nr. des Teilprojektes
(10 - 20 incl. Kolloquium)
Bezeichnung des Teilprojektes
Kalenderwoche des Jahres = zeitl. Lage
Laufende Woche der Arbeit seit Start => Dauer
planbare Ausfallzeiten
(selbst, Partner, Prüfer)
Anmeldetermin = gepl. Abgabetermin
abzgl. x Monate (für BT/DA/MT)
geplanter Abgabetermin
Teilprojekt
Balkenlänge = geschätzte Dauer; kleinste Einheit = 0,5 Wochen
subjektiver Abarbeitungzustand des TP bei korrelierender Besprechung
gepl. Besprechungstermin mit Erstprüfer
Planungsstand des Projektplans (Version, Datum)
spontan + intuitiv geschätzte Dauer des TP;
kleinste Einheit = 0,5 Wochen
Projektplan-Muster für eine Projektarbeit (PA) / Bachelor Thesis (BT) / Diplomarbeit (DA) / Master Thesis (MT)
cc: - Firmen-Betreuer
- PJ-Partner
- Erstprüfer
Empfänger
des PJ-Plans
Plan hier: Bearbeitung wegen Auszeit unterbrechen
Plan hier: Bearbeitung trotz Feiertage fortführen
1
2
2
3
5
4
6
7
8
9
10v
11v

## Project Plan V1.0 (eng.)
The Love Life of Cockchafers at Night
|  | Week of Year | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 35 | 36 | ... | 39
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 26 | 27 | ... | 30
SP No. | SP's Title | Duration
1 | Informative activities / literature | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Writing of thesis | ...
15 | First checking through by examiner | 2
16 | Optimization | 1.5
17 | Colloquium | 1
| Vacation / holidays | [5 empty] | Birth |  |  | Easter |  | Pentecost
| Enrolement / Submission | [7 empty] | March 34 |  |  |  |  | July 34
Meetings
SP = Sub-project
x = f(course of study)
Enrolement
Submission
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.0 / 29.02.2025
Personal Data
Preliminary title
of thesis
SP's number
(10 - 20 SPs incl. Colloquium)
SP's title
Week of year
Weeks since start of project => duration
schedulable time outs
(causes: yourself, partners, examiner, ..)
Date of enrolement = scheduled date of submission minus x months
scheduled date of submission
SP
Length of bar = estimated duration; smallest unit = 0.5 week
Actual state of SP's completion at time of corresponding meeting
(subjective estimation)
Scheduled meeting with first examiner
Project plan of (version / date)
Duration of SP estimated in the beginning
(spontaneously and intuitivly)
smallest unit = 0,5 week
Template for Project Plan of Master's Thesis
cc: - Contact person in company
- Project partner
- First examiner
Receivers of this project plan
Scheduled interruption of work
Scheduled to continue work despite of holiday
Colloquium
1
2
2
3
5
4
6
7
8
9
10v
11v

## Resulting objects
Object Detection with Jetson Nano integrated in a Kuka KR6
Name, Vorname |  |  |  | cc: Firmenbetreuer
Matr.-Nr | <1234567> |  |  | Projektpartner
Erstprüfer
List of all Resulting Objects
Subtask | Resulting objects | done | date
Literature | List of keywords
Brief description of the sources
bib file
Bibliography in the report
pdf documents
quality check
…
Projectplan-Project (10credits) in Master Course "Business Intelligence and Data Analytics"